CEA-UNIVERSITY INSTITUTE

Madrid, Spain

# PM in practice: executing

| Course Code: | MAPM 604 |
| --- | --- |
| Credits: | 3 Credits |
| Academic Level: | Graduate |
| Prerequisites: | PM in Practice - MAPM 601 Introduction to Project Management Standards & Framework - MAPM 602 PM in Practice: Initiating & Planning I - MAPM 603 PM in Practice: Planning II |
| Duration: | 5 Weeks |
| Delivery Format: | Online (Synchronous & Asynchronous Sessions) |
| Total Contact Hours: | Synchronous - 14 hours (3.5 hours/week from week 1 to week 4) - 6 hours for week 5 Asynchronous - 20 hours (4 hours/week from week 1 to week 5) |
| Semester/Term: | [To Be Determined] |
| Professor: | ____________________ |
| Office Hours: | [To Be Determined] |
| Contact: | [To Be Determined] |
| Partner Organization: | Alluvion Games |

# 1. COURSE DESCRIPTION

This course focuses on project execution on dynamic environments by examining how project plans are translated into action, emphasizing and in alignment with the PMBOK® 8th edition in the delivery, team, and stakeholder performance domains, including the tools and techniques of work coordination, sequencing, quality control, and others.

Building on the project plan developed in the previous course – Planning II, students will explore how different approaches, including predictive, agile, and hybrid, support project outcomes.  Although leadership and conflict management is vital in the execution phase, this course dives into methodologies to overcome the challenges for managing dependencies, handling issues, and navigating change during project execution. By the end of the course, students are prepared to lead projects responsibly and adapt delivery decisions to enhance project value.

# 2. COURSE LEARNING OUTCOMES

Upon successful completion of this course, students will be able to:

- Analyze the methodologies such as agile, predictive, and others to support delivery practices based on project context. [Analyze]

- Evaluate the required work in the project plan by coordinating the effort to manage tasks, dependencies, information flow, priorities, and issues and using structured approaches to execute the project. [Evaluate]

- Discuss agile methodology and practice by exploring best practices and approaches, such as Scrum to support iterative delivery, work prioritization, and adaptive change response during the project execution phase. [Understand]

- Formulate an engagement strategy to implement and execute project communication to support the work progression, decision-making, and issue resolution during delivery. [Create]

- Examine quality control tools and techniques to verify deliverables, address defects, and support change decisions while maintaining delivery momentum. [Evaluate]

- Revise the workflow and work packages in response to uncertainty and emerging conditions to balance scope, time, cost, resources, and stakeholder expectations, driving project delivery. [Create]

# 3. REQUIRED MATERIALS

## 3.1 Primary Textbook

- PMBOK® Guide Eighth Edition. (2025). A Guide to the Project Management Body of Knowledge. Newtown Square, Pennsylvania: Project Management Institute.

- Watt, A. (2014). Project Management. Victoria, BC.: BCcampus: Retrieved from https://open-textbc.ca/projectmanagement/.

- Wysocki, R. K. (2011). Effective project management: traditional, agile, extreme. John Wiley & Sons.

## 3.2 Supplementary Textbook

- N/A

## 3.3 Open Educational Resources (OER)

- Agile Business Consortium. (n.d.). Case study: ING’s digital platform tribe goes agile.
https://www.agilebusiness.org/resource-report/case-study-ings-digital-platform-tribe-goes-agile.html

- Alaidaros, H. (2021). The state of the art of agile kanban method: challenges and opportunities. Independent Journal of Management & Production.

- Almadhoun, O. (n.d.). Project Management . OER Commons.

- Brechner, E. (2015). Agile project management with Kanban. Pearson Education.

- Burrows, M. (2014). Kanban from the inside: Understand the Kanban Method, connect it to what you already know, succeed with it (2nd ed.). Blue Hole Press.

- Engwall, M., & Jerbrant, A. (2003). The resource allocation syndrome: the prime challenge of multi-project management?. International journal of project management, 21(6), 403-409. https://doi.org/10.1016/S0263-7863(02)00113-8

- Scrum.org. (2019). The Kanban guide for Scrum teams. Scrum.org.

https://scrumorg-website-prod.s3.amazonaws.com/drupal/2021-01/01-2021%20Kanban%20Guide.pdf?nexus-file=https%3A%2F%2Fscrumorg-website-prod.s3.amazonaws.com%2Fdrupal%2F2021-01%2F01-2021%2520Kanban%2520Guide.pdf

- Too, E. G., & Weaver, P. (2014). The management of project management: A conceptual framework for project governance. International journal of project management, 32(8), 1382-1394. https://doi.org/10.1016/j.ijproman.2013.07.006

## 3.4 Technology Requirements

- Reliable internet connection for synchronous sessions

- Computer with webcam and microphone

- Access to CEA Learning Management System (LMS)

- Microsoft Office Suite or Google Workspace

- MS Project Software

# 4. ASSESSMENT STRUCTURE

This course employs both formative and summative assessments to support learning and evaluate mastery of course objectives.

| Assessment Component | Weight | Type |
| --- | --- | --- |
| Participation & Engagement | 15% | Ongoing |
| Weekly Quizzes (Summative 1) | 20% | Summative |
| Discussion Forums (Formative 1) | 15% | Formative |
| Case Study (Summative 2) | 10% | Summative |
| Term Project: Final Proposal Written Report (Summative 3) | 25% | Summative |
| Term Project Presentation | 15% | Summative |
| TOTAL | 100% |  |

## 4.1 University Grading Scale

| A 93 – 100% | A- 90 – 92% | B+ 87 – 89% | B 83 – 86% | D 60 – 69% |
| --- | --- | --- | --- | --- |
| B- 80 – 82% | C+ 77 – 79% | C 73 – 76% | C- 70 – 72% | F 0 – 59% |
| Passing grade is C- (70%) or higher |  |  |  |  |

# 5. COURSE SCHEDULE

| WEEK 1 | Project Execution Overview |
| --- | --- |
| Topics | - Project Execution (PMBOK® 8th edition: Section 4, 4.5.3 – Executing Focus Area) - Focus area and performance domain intersect (PMBOK® 8th edition: Table 2-1 PM Focus Area & Performance Domain) - Review performance domains: governance, stakeholders, resources, and risk |
| Readings | - PMBOK® 8th edition: - Section 4, 4.5.3 – Executing Focus Area - Table 2-1 Mapping PM Focus Areas & Performance Domains - Watt, A. (2014). Project Management. Victoria, BC.: BCcampus: Retrieved from https://open-textbc.ca/projectmanagement/. - Chapter 17 – Project Implementation Overview |
| Activities | Synchronous: - Course introduction, - Icebreaker activity, - Discussions on: - Why project plan fails during execution? - Information flow during project execution - Work packages and sequencing under resource constraints Asynchronous: - Week 1 Quiz |
| WEEK 2 | Project Execution Methodologies |
| Topics | - Delivery performance domain - Agile, predictive, and hybrid delivery models guided by PMBOK® 8th edition - Agile execution practices (Scrum) - Kanban execution concepts |
| Readings | - PMBOK® 8th edition: - Section 2, 2.1.7 – Tailoring Considerations to 2.1.9 – Check Results - Section 4, 4.2.1 – Predictive Approaches to 4.2.3 – Hybrid Approaches - Section 4, 4.5.3 – Executing Focus Area - Table 2-1 Mapping PM Focus Areas & Performance Domains - Burrows, M. (2014). Kanban from the inside: Understand the Kanban Method, connect it to what you already know, succeed with it (2nd ed.). Blue Hole Press. - Chapter 13 – Agile - Scrum.org. (2019). The Kanban guide for Scrum teams. Scrum.org. https://scrumorg-website-prod.s3.amazonaws.com/drupal/2021-01/01-2021%20Kanban%20Guide.pdf?nexus-file=https%3A%2F%2Fscrumorg-website-prod.s3.amazonaws.com%2Fdrupal%2F2021-01%2F01-2021%2520Kanban%2520Guide.pdf - Wysocki, R. K. (2011). Effective project management: traditional, agile, extreme. John Wiley & Sons. - Chapter 12 – Agile Project Management |
| Activities | Synchronous: - Discussions on: - Compare & contrast agile, predictive, and hybrid execution approaches - Is there any approach that can outperform the others? Asynchronous: - Week 2 Quiz - Discussion forum #1 |
| WEEK 3 | Managing Dependencies |
| Topics | - Review performance domains: delivery and stakeholder - Dependency and activities coordination tools - Issue management tools and resolution paths - Project status reporting and communication (stakeholder feedback loops) - Quality control (defect, rework, adjustment) |
| Readings | - PMBOK® 8th edition: - Section 4, 4.5.3 – Executing Focus Area - Table 2-1 Mapping PM Focus Areas & Performance Domains - Burrows, M. (2014). Kanban from the inside: Understand the Kanban Method, connect it to what you already know, succeed with it (2nd ed.). Blue Hole Press. - Chapter 22 – Designing Kanban Systems - Chapter 23 – Roll Out - Wysocki, R. K. (2011). Effective project management: traditional, agile, extreme. John Wiley & Sons. - Chapter 11 – Complexity and Uncertainty in the Project Landscape |
| Activities | Synchronous: - Discussions on - Which dependency matters most at the project execution phase? - What are the options when roadblock is encountered? - When delivery fails, is it a planning or execution issue? How do you determine the root cause? Asynchronous: - Week 3 Quiz - Discussion forum #2 |
| WEEK 4 | Managing Risk, Resources, and Change |
| Topics | - Review performance domains: delivery and measurement - Managing uncertainty during delivery - Risk recognition & management (qualitative and quantitative) - Resource management (shortages, overload) - Change control and management |
| Readings | - PMBOK® 8th edition: - Section 4, 4.5.3 – Executing Focus Area - Table 2-1 Mapping PM Focus Areas & Performance Domains - Burrows, M. (2014). Kanban from the inside: Understand the Kanban Method, connect it to what you already know, succeed with it (2nd ed.). Blue Hole Press. - Chapter 19 – Analyze Demand and Capability Chapter 23 – Roll Out |
| Activities | Synchronous: - Discussions on: - Resource shortages: poor planning or true shortage? How do you know? - When multiple risks surface during project execution, which one(s) require immediate attention? Asynchronous: - Week 4 Quiz - Discussion forum #3 |
| WEEK 5 | Case Study and Term Project |
| Topics | - Project plan presentation |
| Readings | - N/A |
| Activities | Synchronous: - Project presentation Asynchronous: - ING case study report - Project plan - Peer evaluation |

# 6. ASSIGNMENT DESCRIPTIONS

## 6.1 Participation & Engagement (15%)

Objective: Demonstrate active engagement with course materials and contribute meaningfully to the learning community.

Requirements:

- Attend the synchronous sessions with camera on

- Complete all asynchronous activities and check-ins within specified deadlines

- Contribute substantively to class discussions demonstrating preparation

- Engage respectfully with peers and demonstrate professional conduct

Evaluation: Students receive ongoing feedback throughout the semester by the professor.

## 6.2 Weekly Quizzes – Summative Assessment 1 (20%)

Objective: Assess students’ understanding of key concepts and principles introduced each week.

Requirements:

- Study weekly assigned materials

- Complete it in LMS

Format:

- Multiple choices and true/false questions

- 30 questions x 1 point each = 30 points

Duration: 90 minutes | Online proctored | Open notes (no internet searches)

Due Date: Week 1 to Week 4

LOs Addressed: LO1 to LO6

## 6.3 Discussion Forum – Formative Assessment 1 (15%)

Objective: Encourage an open dialogue for peer learning and develop critical thinking skills by connecting course concepts, exchanging perspectives, and applying knowledge to project challenges.

Requirements (Three Discussion Forums):

- Forum 1 (Week 2): "Describe a scenario in the execution where a hybrid approach would be more effective than agile and predictive only. Provide your rationales."

- Forum 2 (Week 3): "What information should you communicate with the stakeholders during execution to enable timely decisions without slowing down or over communicate?"

- Forum 3 (Week 4): “How do you decide the information require a formal change decision? Who should decide?”

Each Forum Requires:

- Initial post (300-400 words) responding to the prompt with evidence from readings

- Two substantive responses (150-200 words each) to peers

- Engagement with at least one external source not assigned in readings

LOs Addressed: LO2, LO3, LO4, LO5, and LO6

## 6.4 Self-Reflection case study – Summative Assessment 2 (10%)

Objective: Using a case study is to present an opportunity for students to analyze how agile methods are used to coordinate work, respond to change, and deliver project outcomes during the execution phase.

Requirements:

Written Report (1,000 and 1,500 words):

- Executive Summary (250-300 words):

- Body of the Report (750-1,200 words):

- APA: as needed

Due: Week 5

LOs Addressed: LO1, LO3 and LO6

# 7. TERM PROJECT

Summative Assessment 2 (25% Written + 15% Presentation = 40% Total)

## 7.1 Project Overview

Alluvion Games has formally approved the project plan that you submitted in MAPM 603 – PM in Practice Planning II. The objective in this project execution phase is to translate the approved project plan into coordinated, actionable items. By completing this term project, students will demonstrate how execution decisions, risk responses, communication, and workflow adaptation support project outcomes.

## 7.2 Learning Outcomes Addressed

- LO1: Analyze the methodologies such as agile, predictive, and others to support delivery practices based on project context.

- LO2: Evaluate the required work in the project plan by coordinating the effort to manage tasks, dependencies, information flow, priorities, and issues and using structured approaches to execute the project.

- LO3: Discuss agile methodology and practice by exploring best practices and approaches, such as Scrum to support iterative delivery, work prioritization, and adaptive change response during the project execution phase.

- LO4: Formulate an engagement strategy to implement and execute project communication to support the work progression, decision-making, and issue resolution during delivery.

- LO5: Examine quality control tools and techniques to verify deliverables, address defects, and support change decisions while maintaining delivery momentum.

- LO6: Revise the workflow and work packages in response to uncertainty and emerging conditions to balance scope, time, cost, resources, and stakeholder expectations, driving project delivery.

## 7.3 Scenario Context

As a trusted consultant who reports to the Project Sponsor at Alluvion Games, you continue to support the standardization of project reporting templates across the organization to improve consistency, visibility, and decision-making.

The approved project plan has now entered the execution phase. You are required to execute the project plan and not redesign it. Given this project scenario, the following assumptions are:

- Cross-functional teams are contributing to the design of the reporting templates content.

- Stakeholders have competing priorities. Their schedules are limited for meetings.

- Resources are committed and shared across departments.

- Risks and constraints are emerging.

## 7.4 Project Deliverables and Requirements

Part 1: Project Execution Requirements

You have been tasked to execute the project plan. As such, you will demonstrate how execution is managed by addressing the following.

- Execution approach (agile, predictive, or hybrid).

- Nature of the approach and your justification.

- How work packages are sequenced, coordinate, and tracked.

- The key dependencies that affect delivery.

- Project execution issues (two to three issues).

- How these issues will be resolved or escalated.

- Resources constraints or risks, competing priorities, or capacity overload.

- Risk response and trade-offs plan.

- Communication execution plan.

- Workflow or resource plan adjustment.

- Other items that are pertinent in execution.

Due: Week 5

Part 2: Executive Presentation (15 minutes + 5 minutes Q&A):

Based on your project plan in Part 1, you are tasked to present it to the senior management at Alluvion Games.

- Professional slide deck (12-15 slides maximum)

- Clear articulation of key strategic decisions

- Ability to respond to questions about implementation

- Professional presentation delivery

Due: Week 5

LOs Addressed: LO1 to LO6.

## 7.5 Submission Guidelines

- Written Report: Submit via LMS as PDF; APA format; 12pt font; 1.5 line spacing

- Presentation: PowerPoint/Google Slides uploaded 24 hours before presentation

- Citations: Minimum 8 academic/professional sources (excluding textbook)

# 8. ASSESSMENT RUBRICS

## 8.1 Discussion Forum Rubric (100 points per forum)

| Criteria | Excellent (4) | Good (3) | Satisfactory (2) | Needs Improvement (1) | Points |
| --- | --- | --- | --- | --- | --- |
| Initial Post Quality | Demonstrates deep understanding; original insights; multiple sources integrated seamlessly | Shows solid understanding; good use of sources; clear argument | Basic understanding; limited sources; argument needs development | Surface-level response; missing sources; unclear argument | /40 |
| Peer Engagement | Responses advance discussion; pose thoughtful questions; build on peer ideas constructively | Responses add value; engage meaningfully with peer ideas | Basic responses; limited engagement with peer ideas | Superficial responses; no meaningful peer engagement | /35 |
| Timeliness & Professionalism | All posts on time; professional tone; facilitates inclusive dialogue | Posts on time; professional; contributes positively | Some late posts; professional; minimal facilitation | Late posts; unprofessional tone; does not facilitate | /25 |
| TOTAL |  |  |  |  | /100 |

## 8.2 Term Project Grading Rubric (100 points)

| Criteria | Excellent (4) | Good (3) | Satisfactory (2) | Needs Improvement (1) | Points |
| --- | --- | --- | --- | --- | --- |
| Application to Knowledge - Concepts or tools is focused. - Subject is comprehensive. - Report provides specifics, clarity and depth. | Exceptional application of concepts or tools; subject matter is comprehensive, well-integrated, and focused; report provides strong specifics, clarity, and depth. | Solid application of concepts or tools; subject matter is generally comprehensive, well-integrated, and focused; report provides adequate specifics, clarity, and depth. | Basic application of concepts or tools; subject matter is limited; report lacks depth and clear focus. | Minimal or incorrect application of concepts or tools; subject matter is superficial and unclear; report lacks specifics, clarity, and depth. | /45 |
| Content & Requirements Complete - Content is relevant. - Paper completes requirements. | Content is relevant and fully addresses all assignment requirements; expectations are met or exceeded. | Content is relevant and addresses most assignment requirements. | Content partially addresses assignment requirements; Some required elements are missing or underdeveloped. | Content is irrelevant or incomplete; significant requirements are missing. | /15 |
| Analytical & Critical Thinking - Analyzes & provides facts. - Analysis is well-thought out. | Strong analytical and critical thinking; analysis is logical, well-supported with facts or evidence. | Good analytical thinking; analysis is generally well-reasoned and supported. Some points could be more throughout. | Limited analytical thinking; discussion is more descriptive than analytical with weak or inconsistent support. | Little to no analytical thinking; arguments are unsupported or unclear. | /30 |
| Writing & Sources | Publication-quality writing; flawless citations; exceptional sources | Clear, professional writing; appropriate citations | Adequate writing; some citation issues | Poor writing quality; citation problems | /10 |
| TOTAL |  |  |  |  | /100 |

## 8.3 Term Project Presentation Rubric (100 points)

| Criteria | Excellent (4) | Good (3) | Satisfactory (2) | Needs Improvement (1) | Points |
| --- | --- | --- | --- | --- | --- |
| Content & Organization | Key points expertly synthesized; logical flow; compelling narrative | Main points clear; good organization; coherent structure | Content adequate; some organizational issues | Content unclear; poor organization | /30 |
| Visual Design | Professional, polished slides; effective visuals; appropriate text density | Clean design; good visuals; readable | Basic design; some visual issues | Poor design; cluttered or hard to read | /20 |
| Delivery & Presence | Confident, engaging delivery; excellent eye contact; natural pacing | Clear delivery; good presence; appropriate pace | Adequate delivery; some nervousness; pacing issues | Poor delivery; reads slides; significant issues | /25 |
| Q&A Response | Handles questions with expertise; provides insightful elaboration | Responds well to questions; demonstrates understanding | Adequate responses; some difficulty | Unable to respond adequately to questions | /25 |
| TOTAL |  |  |  |  | /100 |

# 9. COURSE POLICIES

## 9.1 Attendance and Participation

Active participation is essential in this online learning environment. Students are expected to enable the cameras for the synchronous sessions. Attendance will be recorded. Asynchronous activities must be completed within specified deadlines. If you anticipate an absence, please notify the professor in advance. Synchronous sessions may be recorded for students who are unable to attend due to documented circumstances. If you anticipate an absence, please notify the professor in advance.

## 9.2 Late Submission Policy

Assignments submitted late will be penalized without prior approval. Extensions may be granted for documented emergencies or extenuating circumstances if requested before the deadline, where possible. Effective time management is required. Review the weekly course schedule and consult with the professor for details.

## 9.3 Academic Integrity

CEA-University Institute maintains the highest standards of academic integrity. All work submitted must be your own. Plagiarism, cheating, or any form of academic dishonesty will result in disciplinary action, which may include a failing grade for the assignment or course. Properly cite all sources using APA format. When in doubt, cite.

## 9.4 Use of Artificial Intelligence (AI) Tools

The use of AI tools (such as ChatGPT, Claude, Gemini) is permitted for brainstorming, research assistance, and editing support. However, all submitted work must represent your own thinking and writing. If you use AI tools, you must: (1) disclose AI use in your submission; (2) include AI-generated content as properly cited material; and (3) be prepared to explain and defend any content in your submissions. AI should augment, not replace, your learning.

## 9.5 Communication Policy

Professors will respond to students’ inquiries and assignments in a timely fashion. Students should check their emails and the learning portal regularly for the updates. Consult with your professor if any clarification is needed.

## 9.6 Technology Requirements and Support

Students must have reliable internet access and appropriate hardware for video conferencing. Technical difficulties should be reported immediately to both the professor and IT support. It is the student's responsibility to ensure familiarity with the LMS and required tools before assignment deadlines.

## 9.7 Accessibility and Accommodations

CEA-University Institute is committed to providing equal access to education for all students. Students requiring accommodations due to a disability should contact the Accessibility Services Office and notify the professor within the first two weeks of class. Accommodations will be provided in accordance with institutional policies and applicable regulations.

## 9.8 Netiquette and Online Conduct

All interactions in this course should reflect professionalism and respect. This includes synchronous sessions, discussion forums, and email communication. Treat all participants with dignity and courtesy. Disagreement is welcome; disrespect is not. Students are expected to maintain appropriate professional conduct in all course-related interactions.

# 10. ADDITIONAL RESOURCES

## 10.1 Academic Support

- CEA Writing Center: ______@cea.edu

- Library Research Support: _____@cea.edu

- Academic Advising: _____@cea.edu

- IT Help Desk: _____@cea.edu

## 10.2 Professional Development Resources

- Harvard Business Review (institutional access)

- LinkedIn Learning (free for CEA students)

- Coursera for Campus partnerships

- Management professional associations (PMI student memberships)

# 11. SYLLABUS DISCLAIMER

This syllabus provides a general plan for the course. The professor reserves the right to modify the syllabus as needed to respond to pedagogical needs, current events, or unforeseen circumstances. Students will be notified of any significant changes via the LMS and class announcements. It is the student's responsibility to remain informed of any modifications.

CEA-University Institute | Madrid, Spain |

This syllabus is subject to change. Students will be notified of any modifications.

© 2026 Alluvion Games LLC. All rights reserved.