CEA-UNIVERSITY INSTITUTE

Madrid, Spain

# PM in practice: monitoring & control, and closing

| Course Code: | MAPM 605 |
| --- | --- |
| Credits: | 3 Credits |
| Academic Level: | Graduate |
| Prerequisites: | PM in Practice - MAPM 601 Introduction to Project Management Standards & Framework - MAPM 602 PM in Practice: Initiating & Planning I - MAPM 603 PM in Practice: Planning II - MAPM 604 PM in Practice: Executing |
| Duration: | 5 Weeks |
| Delivery Format: | Online (Synchronous & Asynchronous Sessions) |
| Total Contact Hours: | Synchronous - 14 hours (3.5 hours/week from week 1 to week 4) - 6 hours for week 5 Asynchronous - 20 hours (4 hours/week from week 1 to week 5) |
| Semester/Term: | [To Be Determined] |
| Professor: | ____________________ |
| Office Hours: | [To Be Determined] |
| Contact: | [To Be Determined] |
| Partner Organization: | Alluvion Games |

# 1. COURSE DESCRIPTION

This course focuses on how a project’s performance is being measured, monitored & controlled, and formally closed. In alignment with the PMBOK® 8th edition, this course emphasizes monitoring & control and closing, which are the final two phases of the project lifecycle. These processes of the decision support activities are vitally important to ensure value realization and capture organizational learning.

Building on the project execution phase from the previous course, students will explore the tools and techniques for performance measurement, variance analysis, risk monitoring, and change control practices. These are critical steps to guide corrective and preventative actions during the monitoring and control phase. Students will continue learning what it takes for project closing, which addresses stakeholder acceptance, lessons-learned, and knowledge transfer to operations. By the end of this course, students will apply the knowledge to practical assignments to demonstrate the effectiveness of monitoring & control and closing guiding the project value and supporting continuous improvement.

# 2. COURSE LEARNING OUTCOMES

Upon successful completion of this course, students will be able to:

- Analyze tools and techniques to evaluate, assess progress, variance, and delivery for project performance. [Analyze]

- Evaluate performance variance in scope, schedule, cost, quality, and risk to determine an appropriate cause of action. [Evaluate]

- Implement integrated change control process to assess and manage approved changes. [Apply]

- Assess risks and issues to determine escalation and response decisions. [Evaluate]

- Measure project outcomes and evaluate if they meet acceptance criteria and contribute to intended benefits and value realization. [Evaluate]

- Synthesize project closing activities, including lessons-learned and other key activities to support organizational learning and transition to operations. [Create]

# 3. REQUIRED MATERIALS

## 3.1 Primary Textbook

- PMBOK® Guide Eighth Edition. (2025). A Guide to the Project Management Body of Knowledge. Newtown Square, Pennsylvania: Project Management Institute.

- Watt, A. (2014). Project Management. Victoria, BC.: BCcampus: Retrieved from https://open-textbc.ca/projectmanagement/.

## 3.2 Supplementary Textbook

- N/A

## Open Educational Resources (OER)

- Almadhoun, O. (n.d.). Project Management . OER Commons.

- De Marco, A., & Narbaev, T. (2013). Earned value‐based performance monitoring of facility construction projects. Journal of facilities Management, 11(1), 69-80 https://doi.org/10.1108/14725961311301475

- Flyvbjerg, B. (2014). What you should know about megaprojects and why: An overview. Project management journal, 45(2), 6-19. https://doi.org/10.1002/pmj.21409

- Kloppenborg, T. J., Tesch, D., & Manolis, C. (2014). Project success and executive sponsor behaviors: Empirical life cycle stage investigations. Project Management Journal, 45(1), 9-20. https://doi.org/10.1002/pmj.21396

- Meredith, J. R., Shafer, S. M., & Mantel Jr, S. J. (2017). Project management: a strategic managerial approach. John Wiley & Sons.

- Müller, R., & Lecoeuvre, L. (2014). Operationalizing governance categories of projects. International Journal of Project Management, 32(8), 1346-1357.        https://doi.org/10.1016/j.ijproman.2014.04.005

- Perminova, O., Gustafsson, M., & Wikström, K. (2008). Defining uncertainty in projects–a new perspective. International journal of project management, 26(1), 73-79. https://doi.org/10.1016/j.ijproman.2007.08.005

- Shenhar, A. J., Dvir, D., Levy, O., & Maltz, A. C. (2001). Project success: a multidimensional strategic concept. Long range planning, 34(6), 699-725. https://doi.org/10.1016/S0024-6301(01)00097-8

- Ward, S., & Chapman, C. (2003). Transforming project risk management into project uncertainty management. International journal of project management, 21(2), 97-105. https://doi.org/10.1016/S0263-7863(01)00080-1

- Williams, T. (2008). How do organizations learn lessons from projects—And do they?. IEEE Transactions on engineering management, 55(2), 248-266. https://doi.org/10.1109/TEM.2007.912920

## 3.4 Technology Requirements

- Reliable internet connection for synchronous sessions

- Computer with webcam and microphone

- Access to CEA Learning Management System (LMS)

- Microsoft Office Suite or Google Workspace

- MS Project Software

# 4. ASSESSMENT STRUCTURE

This course employs both formative and summative assessments to support learning and evaluate mastery of course objectives.

| Assessment Component | Weight | Type |
| --- | --- | --- |
| Participation & Engagement | 15% | Ongoing |
| Weekly Quizzes (Summative 1) | 20% | Summative |
| Discussion Forums (Formative 1) | 15% | Formative |
| Self-Reflection Case Study (Summative 2) | 10% | Summative |
| Term Project: Final Proposal Written Report (Summative 3) | 25% | Summative |
| Term Project Presentation | 15% | Summative |
| TOTAL | 100% |  |

## 4.1 University Grading Scale

| A 93 – 100% | A- 90 – 92% | B+ 87 – 89% | B 83 – 86% | D 60 – 69% |
| --- | --- | --- | --- | --- |
| B- 80 – 82% | C+ 77 – 79% | C 73 – 76% | C- 70 – 72% | F 0 – 59% |
| Passing grade is C- (70%) or higher |  |  |  |  |

# 5. COURSE SCHEDULE

| WEEK 1 | Monitoring & Control: Performance Measurement & Variance |
| --- | --- |
| Topics | - Project Monitoring and Controlling (Section 4, 4.5.4 – Monitoring & Controlling Focus Area) - Focus area and performance domain intersect (Table 2-1 PM Focus Area & Performance Domain) - Review performance domains: finance, schedule, and resources - Earned value management - Trend analysis - Resource and cost performance analysis |
| Readings | - PMBOK® 8th edition: - Section 4, 4.5.4 – Monitoring & Controlling Focus Area - Table 2-1 Mapping PM Focus Areas & Performance Domains - Watt, A. (2014). Project Management. Victoria, BC.: BCcampus: Retrieved from https://open-textbc.ca/projectmanagement/. - Earned value management, p137 – 145 - De Marco, A., & Narbaev, T. (2013). Earned value‐based performance monitoring of facility construction projects. Journal of facilities Management, 11(1), 69-80 https://doi.org/10.1108/14725961311301475 - Meredith, J. R., Shafer, S. M., & Mantel Jr, S. J. (2017). Project management: a strategic managerial approach. John Wiley & Sons. - Chapter 10: 10.3 – Earned Value Analysis - Using earned value to monitor governmental archiving and records costs p.415. |
| Activities | Synchronous: - Course introduction, - Icebreaker activity, - Discussions on: - EVM analysis interpretation - Which performance indicators support decisions? - How and when to make use of each variance types? Asynchronous: - Week 1 Quiz |
| WEEK 2 | Monitoring & Control: Integrated Change Control & Resources Analysis |
| Topics | - Resources performance domain - Integrated change control - Change request forms - Governance performance domain |
| Readings | - PMBOK® 8th edition: - Section 4, 4.5.4 – Monitoring & Controlling Focus Area - Table 2-1 Mapping PM Focus Areas & Performance Domains - Watt, A. (2014). Project Management. Victoria, BC.: BCcampus: Retrieved from https://open-textbc.ca/projectmanagement/. - Change control, p187 – 188 - Kloppenborg, T. J., Tesch, D., & Manolis, C. (2014). Project success and executive sponsor behaviors: Empirical life cycle stage investigations. Project Management Journal, 45(1), 9-20. https://doi.org/10.1002/pmj.21396 - Müller, R., & Lecoeuvre, L. (2014). Operationalizing governance categories of projects. International Journal of Project Management, 32(8), 1346-1357. https://doi.org/10.1016/j.ijproman.2014.04.005 |
| Activities | Synchronous: - Discussions on: - Evaluate change requests - Change impact assessment and implications - Resources and cost impacts Asynchronous: - Week 2 Quiz - Discussion forum #1 |
| WEEK 3 | Monitoring & Control: Resources, Quality and Risk |
| Topics | - Resources and risks performance domains - Resource utilization - Risk register & tracking - Issue logs - Quality inspection & acceptance |
| Readings | - PMBOK® 8th edition: - Section 4, 4.5.4 – Monitoring & Controlling Focus Area - Table 2-1 Mapping PM Focus Areas & Performance Domains - Watt, A. (2014). Project Management. Victoria, BC.: BCcampus: Retrieved from https://open-textbc.ca/projectmanagement/. - Quality control, p145 – 167 - Risk implementation and closeout p184 – 185 - Perminova, O., Gustafsson, M., & Wikström, K. (2008). Defining uncertainty in projects–a new perspective. International journal of project management, 26(1), 73-79. https://doi.org/10.1016/j.ijproman.2007.08.005 - Ward, S., & Chapman, C. (2003). Transforming project risk management into project uncertainty management. International journal of project management, 21(2), 97-105. https://doi.org/10.1016/S0263-7863(01)00080-1 - Wysocki, R. K. (2011). Effective project management: traditional, agile, extreme. John Wiley & Sons. - Chapter 11 – Complexity and Uncertainty in the Project Landscape |
| Activities | Synchronous: - Discussions on - When do resource constraints become risk? - What are the most critical resource risks and proposed risk responses? Asynchronous: - Week 3 Quiz - Discussion forum #2 |
| WEEK 4 | Project Closing: Lessons-Learned and Knowledge Transfer |
| Topics | - Resources performance domain - Project closure checklist - Performance review and final report - Resource released plan - Lessons learned - Knowledge transfer and operations handover documentations - Formal acceptance documentation |
| Readings | - PMBOK® 8th edition: - Section 4, 4.5.5 – Project Closing Focus Area - Table 2-1 Mapping PM Focus Areas & Performance Domains - Watt, A. (2014). Project Management. Victoria, BC.: BCcampus: Retrieved from https://open-textbc.ca/projectmanagement/. - Project completion, p189 – 194 - Williams, T. (2008). How do organizations learn lessons from projects—And do they?. IEEE Transactions on engineering management, 55(2), 248-266. https://doi.org/10.1109/TEM.2007.912920 |
| Activities | Synchronous: - Discussions on: - How and when to release resources? - How and when to transfer ownership to operations? - What are the challenges in capturing in lessons learned? Asynchronous: - Week 4 Quiz - Discussion forum #3 |
| WEEK 5 | Case Study and Term Project |
| Topics | - Project plan presentation |
| Readings | - TBA |
| Activities | Synchronous: - Project presentation Asynchronous: - Case study report - Project plan - Peer evaluation |

# 6. ASSIGNMENT DESCRIPTIONS

## 6.1 Participation & Engagement (15%)

Objective: Demonstrate active engagement with course materials and contribute meaningfully to the learning community.

Requirements:

- Attend the synchronous sessions with camera on

- Complete all asynchronous activities and check-ins within specified deadlines

- Contribute substantively to class discussions demonstrating preparation

- Engage respectfully with peers and demonstrate professional conduct

Evaluation: Students receive ongoing feedback throughout the semester by the professor.

## 6.2 Weekly Quizzes – Summative Assessment 1 (20%)

Objective: Assess students’ understanding of key concepts and principles introduced each week.

Requirements:

- Study weekly assigned materials

- Complete it in LMS

Format:

- Multiple choices and true/false questions

- 30 questions x 1 point each = 30 points

Duration: 90 minutes | Online proctored | Open notes (no internet searches)

Due Date: Week 1 to Week 4

LOs Addressed: LO1 to LO6

## 6.3 Discussion Forum – Formative Assessment 1 (15%)

Objective: Encourage an open dialogue for peer learning and develop critical thinking skills by connecting course concepts, exchanging perspectives, and applying knowledge to project challenges.

Requirements (Three Discussion Forums):

- Forum 1 (Week 2): "Do all change requests require project sponsor approval or governance escalation?"

- Forum 2 (Week 3): "Why do issue logs fail to prevent problems? How can they be used more effectively? "

- Forum 3 (Week 4): "Can resource release and knowledge transfer create project risk at the closing stage? How?”

Each Forum Requires:

- Initial post (300-400 words) responding to the prompt with evidence from readings

- Two substantive responses (150-200 words each) to peers

- Engagement with at least one external source not assigned in readings

LOs Addressed: LO2, LO3, LO4, LO5, and LO6

## 6.4 Self-Reflection case study – Summative Assessment 2 (10%)

Objective: The earned value assignment is to develop students’ ability to interpret earned value management (EVM) performance and use the data to support decision-making. Students are to provide a qualitative report by interpretating a high-level earned value summary and what actions should be taken. Calculations of the earned value is not required.  Therefore, the written report is to articulate a short performance interpretation to support decision-making.

Requirements:

Written Report (1,000 and 1,500 words):

- Executive Summary (250-300 words):

    - Overview of the case and the purpose of the report.

- Body of the Report (750-1,200 words):

- APA: as needed

Due: Week 5

LOs Addressed: LO1, LO2 and LO4

# 7. TERM PROJECT

Summative Assessment 2 (25% Written + 15% Presentation = 40% Total)

## 7.1 Project Overview

Alluvion Games is implementing a Standardized Project Reporting Template across all departments to improve consistency, transparency, comparability, and decision-making.

In the previous phases (courses), the project has completed the following:

- Developed the business case.

- Built a project management plan.

- Designed a project execution approach.

- Defined dependencies, risk responses, and resource allocations.

## 7.2 Learning Outcomes Addressed

- LO1: Analyze tools and techniques to evaluate, assess progress, variance, and delivery for project performance.

- LO2: Evaluate performance variance in scope, schedule, cost, quality, and risk to determine an appropriate cause of action.

- LO3: Implement integrated change control process to assess and manage approved changes.

- LO4: Assess risks and issues to determine escalation and response decisions.

- LO5: Measure project outcomes and evaluate if they meet acceptance criteria and contribute to intended benefits and value realization.

- LO6: Synthesize project closing activities, including lessons-learned and other key activities to support organizational learning and transition to operations.

## 7.3 Scenario Context

As a trusted consultant who reports to the Project Sponsor at Alluvion Games, you have been tasked to provide an independent review to the Steering Committee team. This review is to ensure:

- Whether control mechanisms function effectively.

- Whether risks are managed appropriately.

- Whether the project is ready for closure.

## 7.4 Project Deliverables and Requirements

Part 1: Monitoring and Controlling – Scenario One

Assuming the project has a timeline of 12 months to completion. The project is 9 months into the monitoring and controlling phase. With the remaining 3 months, a major risk has now materialized.

The emerging situations are:

- Two large departments have decided that they will not fully adopted the standardized project report template unless:

  - Their legacy reporting fields are preserved.

  - Custom template for their departments is allowed.

  - Implementation deadline is extended for another 6 months.

- The lead Business Analyst has resigned.

- One of the SME has been reassigned to another pressing project.

- Informal adjustments to template structure without formal change requests have already occurred.

- The risk register identified “adoption resistance” as a moderate risk.

- The mitigation strategy was to enhance communication. However, the actual communication was limited.

The project sponsor stressed that “we need to deliver this project on time. Adjust where necessary.”

In light of the above situations, prepare a structured response by addressing below:

- Risk & monitoring assessment

  - Were these risks foreseeable?

  - Were monitoring and controlling mechanisms adequate?

  - Were the early warning signals exist or ignored?

- Control & governance evaluation

  - Has the steering committee been bypassed?

  - Has the escalation process been followed or bypassed?

  - What the communication between the project manager and project sponsor?

- Recommended action

  - Based on these emerging issues surfaced three months before project closure, what would you recommend to bring the project back on track?

Part 2: Project Closing – Scenario Two

Assumptions in scenario two are as follows:

- Scenarios One and Two are not connected.

- The standardized project report template has now been delivered.

- The project is now in the closing phase.

The emerging situations are:

- Adoption rates were very lo across departments.

- Some departments continue to use the legacy reports.

- Departments claimed that training was insufficient.

- Lessons learned sessions were organized. But the attendance was limited.

- Several project team members have already been released.

The project sponsor asked:

- Can we close this project formally?

In light of the above situations, evaluate whether the project is ready for closure by addressing below:

- Delivery assessment

  - Was training plan be considered in the project plan?

  - Is formal acceptance sufficient?

- Resource & knowledge transfer evaluation

  - Has operational transition been properly addressed in the project plan?

  - How can knowledge transfer sessions be stabilized?

- Recommended action

  - Close as planned?

  - Close with new conditions?

  - Project extension?

Part 3: Executive Presentation (15 minutes + 5 minutes Q&A):

Based on the above scenarios, you will present it to the senior management at Alluvion Games.

- Professional slide deck (12-15 slides maximum)

- Clear articulation of key strategic decisions

- Ability to respond to questions about implementation

- Professional presentation delivery

Due: Week 5

LOs Addressed: LO1 to LO6.

## 7.5 Submission Guidelines

- Written Report: Submit via LMS as PDF; APA format; 12pt font; 1.5 line spacing

- Presentation: PowerPoint/Google Slides uploaded 24 hours before presentation

- Citations: Minimum 8 academic/professional sources (excluding textbook)

# 8. ASSESSMENT RUBRICS

## 8.1 Discussion Forum Rubric (100 points per forum)

| Criteria | Excellent (4) | Good (3) | Satisfactory (2) | Needs Improvement (1) | Points |
| --- | --- | --- | --- | --- | --- |
| Initial Post Quality | Demonstrates deep understanding; original insights; multiple sources integrated seamlessly | Shows solid understanding; good use of sources; clear argument | Basic understanding; limited sources; argument needs development | Surface-level response; missing sources; unclear argument | /40 |
| Peer Engagement | Responses advance discussion; pose thoughtful questions; build on peer ideas constructively | Responses add value; engage meaningfully with peer ideas | Basic responses; limited engagement with peer ideas | Superficial responses; no meaningful peer engagement | /35 |
| Timeliness & Professionalism | All posts on time; professional tone; facilitates inclusive dialogue | Posts on time; professional; contributes positively | Some late posts; professional; minimal facilitation | Late posts; unprofessional tone; does not facilitate | /25 |
| TOTAL |  |  |  |  | /100 |

## 8.2 Term Project Grading Rubric (100 points)

| Criteria | Excellent (4) | Good (3) | Satisfactory (2) | Needs Improvement (1) | Points |
| --- | --- | --- | --- | --- | --- |
| Application to Knowledge - Concepts or tools is focused. - Subject is comprehensive. - Report provides specifics, clarity and depth. | Exceptional application of concepts or tools; subject matter is comprehensive, well-integrated, and focused; report provides strong specifics, clarity, and depth. | Solid application of concepts or tools; subject matter is generally comprehensive, well-integrated, and focused; report provides adequate specifics, clarity, and depth. | Basic application of concepts or tools; subject matter is limited; report lacks depth and clear focus. | Minimal or incorrect application of concepts or tools; subject matter is superficial and unclear; report lacks specifics, clarity, and depth. | /45 |
| Content & Requirements Complete - Content is relevant. - Paper completes requirements. | Content is relevant and fully addresses all assignment requirements; expectations are met or exceeded. | Content is relevant and addresses most assignment requirements. | Content partially addresses assignment requirements; Some required elements are missing or underdeveloped. | Content is irrelevant or incomplete; significant requirements are missing. | /15 |
| Analytical & Critical Thinking - Analyzes & provides facts. - Analysis is well-thought out. | Strong analytical and critical thinking; analysis is logical, well-supported with facts or evidence. | Good analytical thinking; analysis is generally well-reasoned and supported. Some points could be more throughout. | Limited analytical thinking; discussion is more descriptive than analytical with weak or inconsistent support. | Little to no analytical thinking; arguments are unsupported or unclear. | /30 |
| Writing & Sources | Publication-quality writing; flawless citations; exceptional sources | Clear, professional writing; appropriate citations | Adequate writing; some citation issues | Poor writing quality; citation problems | /10 |
| TOTAL |  |  |  |  | /100 |

## 8.3 Term Project Presentation Rubric (100 points)

| Criteria | Excellent (4) | Good (3) | Satisfactory (2) | Needs Improvement (1) | Points |
| --- | --- | --- | --- | --- | --- |
| Content & Organization | Key points expertly synthesized; logical flow; compelling narrative | Main points clear; good organization; coherent structure | Content adequate; some organizational issues | Content unclear; poor organization | /30 |
| Visual Design | Professional, polished slides; effective visuals; appropriate text density | Clean design; good visuals; readable | Basic design; some visual issues | Poor design; cluttered or hard to read | /20 |
| Delivery & Presence | Confident, engaging delivery; excellent eye contact; natural pacing | Clear delivery; good presence; appropriate pace | Adequate delivery; some nervousness; pacing issues | Poor delivery; reads slides; significant issues | /25 |
| Q&A Response | Handles questions with expertise; provides insightful elaboration | Responds well to questions; demonstrates understanding | Adequate responses; some difficulty | Unable to respond adequately to questions | /25 |
| TOTAL |  |  |  |  | /100 |

# 9. COURSE POLICIES

## 9.1 Attendance and Participation

Active participation is essential in this online learning environment. Students are expected to enable the cameras for the synchronous sessions. Attendance will be recorded. Asynchronous activities must be completed within specified deadlines. If you anticipate an absence, please notify the professor in advance. Synchronous sessions may be recorded for students who are unable to attend due to documented circumstances. If you anticipate an absence, please notify the professor in advance.

## 9.2 Late Submission Policy

Assignments submitted late will be penalized without prior approval. Extensions may be granted for documented emergencies or extenuating circumstances if requested before the deadline, where possible. Effective time management is required. Review the weekly course schedule and consult with the professor for details.

## 9.3 Academic Integrity

CEA-University Institute maintains the highest standards of academic integrity. All work submitted must be your own. Plagiarism, cheating, or any form of academic dishonesty will result in disciplinary action, which may include a failing grade for the assignment or course. Properly cite all sources using APA format. When in doubt, cite.

## 9.4 Use of Artificial Intelligence (AI) Tools

The use of AI tools (such as ChatGPT, Claude, Gemini) is permitted for brainstorming, research assistance, and editing support. However, all submitted work must represent your own thinking and writing. If you use AI tools, you must: (1) disclose AI use in your submission; (2) include AI-generated content as properly cited material; and (3) be prepared to explain and defend any content in your submissions. AI should augment, not replace, your learning.

## 9.5 Communication Policy

Professors will respond to students’ inquiries and assignments in a timely fashion. Students should check their emails and the learning portal regularly for the updates. Consult with your professor if any clarification is needed.

## 9.6 Technology Requirements and Support

Students must have reliable internet access and appropriate hardware for video conferencing. Technical difficulties should be reported immediately to both the professor and IT support. It is the student's responsibility to ensure familiarity with the LMS and required tools before assignment deadlines.

## 9.7 Accessibility and Accommodations

CEA-University Institute is committed to providing equal access to education for all students. Students requiring accommodations due to a disability should contact the Accessibility Services Office and notify the professor within the first two weeks of class. Accommodations will be provided in accordance with institutional policies and applicable regulations.

## 9.8 Netiquette and Online Conduct

All interactions in this course should reflect professionalism and respect. This includes synchronous sessions, discussion forums, and email communication. Treat all participants with dignity and courtesy. Disagreement is welcome; disrespect is not. Students are expected to maintain appropriate professional conduct in all course-related interactions.

# 10. ADDITIONAL RESOURCES

## 10.1 Academic Support

- CEA Writing Center: ______@cea.edu

- Library Research Support: _____@cea.edu

- Academic Advising: _____@cea.edu

- IT Help Desk: _____@cea.edu

## 10.2 Professional Development Resources

- Harvard Business Review (institutional access)

- LinkedIn Learning (free for CEA students)

- Coursera for Campus partnerships

- Management professional associations (PMI student memberships)

# 11. SYLLABUS DISCLAIMER

This syllabus provides a general plan for the course. The professor reserves the right to modify the syllabus as needed to respond to pedagogical needs, current events, or unforeseen circumstances. Students will be notified of any significant changes via the LMS and class announcements. It is the student's responsibility to remain informed of any modifications.

CEA-University Institute | Madrid, Spain |

This syllabus is subject to change. Students will be notified of any modifications.

© 2026 Alluvion Games LLC. All rights reserved.